## Product Backlog
Sprint 1
Sprint | Epic Number | Epic Name | Feature | User Story | Start Date | End Date | Notes
| E1 | Landing page | Application entry point | Designing the landing page | 2026-02-12 | 2026-02-25
Sprint 1 | E1 | Guest user flow | Browse as guest; view questionnaires | As a guest I would like to interact with sample questionnaires | 2026-02-12 | 2026-02-25 | Complete guest path, no auth required.
Sprint 1 | E1 | Guest user flow | Browse as guest; view questionnaires | As a guest I can start a screening survey without signup | 2026-02-12 | 2026-02-25 | Complete guest path, no auth required.
Sprint 1 | E1 | Guest user flow | Browse as guest; view questionnaires | As a guest I can see severity evaluation dashboard and save answers temporarily | 2026-02-12 | 2026-02-25 | Complete guest path, no auth required.
Sprint 1 | E1 | Guest user flow | Agentic chat | As a guest I would like ti interact with agentic chat | 2026-02-12 | 2026-02-12
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I would like to register with email | 2026-02-12 | 2026-02-25 | Include basic validation and session handling.
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I would like to get successfully authenticated to the system | 2026-02-12 | 2026-02-25 | Include basic validation and session handling.
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I would like to get successfully authorized to the system | 2026-02-12 | 2026-02-25 | Include basic validation and session handling.
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I need to reset my password as required
Sprint 2
Sprint 2 | E3 | Agentic Flow | End user agentic flow | As an end user I would like to interact with agentic chat
Sprint 2 | E3 | Agentic Flow | Clinician agent workflows | As a Clinician I would like to interact with agentic chat | 2026-02-26 | 2026-03-10 | Core agent UI and routing.
Sprint 2 | E3 | Agentic Flow | Clinician agentic workflows | As a Clinician I would like to obtain the end user journey from the agentic chat | 2026-02-26 | 2026-03-10 | Core agent UI and routing.
Sprint 2 | E3 | Agentic Flow | Clinician agentic workflows | As a Clinician I would like to obtain previous employment details of the end user from the agentic chat | 2026-02-26 | 2026-03-10 | Core agent UI and routing.
Sprint 3
Sprint 3 | E3 | Agentic Flow | Organizational agentic workflows | As an employer I would like to interact with agentic chat | 2026-03-11 | 2026-03-25
Sprint 3 | E3 | Agentic Flow | Organizational agentic workflows | As an employer I would like to check the end user journey | 2026-03-11 | 2026-03-25
Sprint 3 | E3 | Agentic Flow | Organizational agentic workflows | As an employer I would like to see the credibility of the learning disorder report | 2026-03-11 | 2026-03-25
Sprint 3 | E3 | Agentic Flow | Organizational agentic workflows | As an employer I would like to see the severity level of the learning disorder | 2026-03-11 | 2026-03-25
Sprint 4
Sprint 4 | E4 | ML Statistical Validation | Threshold tuning & severity bands | As a clinician I can view thresholded severity bands; As a data scientist I can tune thresholds to optimise recall/precision tradeoffs. | 2026-03-26 | 2026-04-15 | Batch evaluation and reporting.
Sprint 4 | E4 | ML Statistical Validation | Validation reports & dashboards | As a stakeholder (non technical)I can view calibration visualisations | 2026-03-26 | 2026-04-15 | Batch evaluation and reporting.

## Efforts & Estimates
Efforts and Estimates
Task | Best Effort (hours) | Optimal Effort (hours) | Worst Effort (hours)
Project Initiation & Planning | 40h | 60h | 120h
Problem Identification | 24h | 30h | 42h
Stakeholder Discussions (initial) | 10h | 15h | 20h
Requirement Analysis | 20h | 25h | 40h
Proposal Preparation & Submission | 8h | 10h | 15h
Business Requirements Document (BRD) | 25h | 30h | 40h
Scope Change & Background Research (post-presentation) | 15h | 20h | 30h
BRD Update (after scope change) | 2h | 3h | 5h
Research & Thesis Writing (ongoing) | 100h | 120h | 200h
Data Collection | 25h | 30h | 40h
Data Cleaning & Preprocessing | 5h | 7h | 10h
Exploratory Data Analysis (EDA) | 5h | 7h | 10h
UI Designing for landing page | 5h | 10h | 30h
Landing page development | 8h | 10h | 20h
QA & Visual testing for landing page | 3h | 4h | 5h
UI Designing for questionnaire page | 10h | 12h | 20h
Implementation of questionnaire page | 8h | 10h
Complete Guest User Flow | 5h | 8h | 10h
QA & Visual testing for questionnaire flow | 5h | 8h | 10h
UI Designing for guest user disorder severity results dashboard | 10h | 15h | 20h
Implementaion of severity results dashboard | 12h | 16h | 20h
QA and visual testing | 8h | 10h | 12h
UI Design of Login & Sign-up | 5h | 8h | 10h
Login & Sign-up Implementation | 8h | 10h | 20h
To be Continued
Database Design & Setup | 9600 (160h) | 12000 (200h) | 19200 (320h)
Backend/API Development & Integration | 21600 (360h) | 26400 (440h) | 38400 (640h)
Identity/Consent Integration | 9600 (160h) | 12000 (200h) | 19200 (320h)
Develop Agentic Flow (Guest & Employee) | 14400 (240h) | 19200 (320h) | 28800 (480h)
CI/CD Pipeline & Containerization | 16800 (280h) | 21600 (360h) | 33600 (560h)
Feature Engineering | 9600 (160h) | 12000 (200h) | 19200 (320h)
Model Training (XGBoost) | 9600 (160h) | 12000 (200h) | 19200 (320h)
Statistical Validation & Metrics (XGBoost) | 9600 (160h) | 12000 (200h) | 19200 (320h)
Disorder Severity Classification Module | 9600 (160h) | 12000 (200h) | 19200 (320h)
Employee Validation & Role Alignment | 7200 (120h) | 9600 (160h) | 14400 (240h)
Data Insights & Visual Dashboards | 7200 (120h) | 9600 (160h) | 14400 (240h)
Security & Privacy Testing | 9600 (160h) | 12000 (200h) | 19200 (320h)
Accessibility Testing (a11y) | 4800 (80h) | 7200 (120h) | 9600 (160h)
Performance / Load Testing | 9600 (160h) | 12000 (200h) | 19200 (320h)
System Integration Testing | 9600 (160h) | 12000 (200h) | 19200 (320h)
User Acceptance Testing (UAT) | 9600 (160h) | 12000 (200h) | 19200 (320h)
Documentation: Technical & API Docs | 43200 (720h) | 55200 (920h) | 81600 (1360h)
Documentation: User Manuals & Training | 14400 (240h) | 16800 (280h) | 24000 (400h)
Training Sessions & Handover | 7200 (120h) | 9600 (160h) | 14400 (240h)
Progress Viva 1 (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h)
Progress Viva 2 (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h)
Final Viva (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h)
System Deployment: Staging | 4800 (80h) | 4800 (80h) | 7200 (120h)
System Deployment: Production | 4800 (80h) | 4800 (80h) | 7200 (120h)
System Testing & Evaluation (full) | 14400 (240h) | 19200 (320h) | 28800 (480h)
Final Thesis Writing & Submission (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h)
Project Closure & Archiving | 2400 (40h) | 2400 (40h) | 4800 (80h)

## Gantt Chart
[28 empty] | Tasks to be done | [8 empty] | Completed tasks
Task | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Project Initiation & Planning | bar: January W1 to January W2
Problem Identification | bar: January W1
Stakeholder Discussions (initial) | bar: January W1 to January W3
Supervisor Meetings & Feedback (biweekly)
Requirement Analysis | bar: January W2 to January W4
Proposal Preparation & Submission | bar: January W3 to January W4
Proposal Presentation | bar: January W4
Business Requirements Document (BRD) | bar: January W4 to February W3
Scope Change & Background Research (post-presentation) | bar: February W1 to March W1
BRD Update (after scope change) | bar: February W2 to March W1
Data Governance & Privacy Plan | bar: February W1 to March W2
Research & Thesis Writing (ongoing) | bar: January W1 to August W3
Start Research Work & Thesis Writing (intensive) | bar: February W1 to August W3
Data Collection | bar: February W1 to April W4
Data Cleaning & Preprocessing | bar: March W1 to May W3
Exploratory Data Analysis (EDA) | bar: March W2 to June W1
UI Designing (Figma) | bar: February W3 to March W4
Prototyping & Usability Testing | bar: March W2 to April W2
Complete Guest User Flow (UX) | bar: March W3 to April W2
Login & Sign-up Implementation | bar: April W1 to April W4
Database Design & Setup | bar: March W3 to April W3
Backend/API Development & Integration | bar: April W1 to June W3
Identity/Consent Integration | bar: April W3 to May W3
Develop Agentic Flow (Guest & Employee) | bar: April W3 to June W2
CI/CD Pipeline & Containerization | bar: June W1 to August W1
Feature Engineering | bar: May W3 to June W3
Model Training (XGBoost) | bar: June W1 to July W1
Statistical Validation & Metrics (XGBoost) | bar: June W3 to July W3
Disorder Severity Classification Module | bar: July W1 to August W1
Employee Validation & Role Alignment | bar: August W1 to August W4
Data Insights & Visual Dashboards | bar: August W3 to September W2
Security & Privacy Testing | bar: September W1 to October W1
Accessibility Testing (a11y) | bar: September W2 to September W4
Performance / Load Testing | bar: September W3 to October W3
System Integration Testing | bar: September W1 to October W1
User Acceptance Testing (UAT) | bar: October W1 to November W1
Documentation: Technical & API Docs | bar: May W3 to November W1
Documentation: User Manuals & Training | bar: September W3 to November W1
Training Sessions & Handover | bar: October W4 to November W3
Progress Viva 1 (Milestone) | bar: April W4
Progress Viva 2 (Milestone) | bar: August W2
Final Viva (Milestone) | bar: November W4
System Deployment: Staging | bar: August W3 to August W4
System Deployment: Production | bar: November W1 to November W2
System Testing & Evaluation (full) | bar: September W1 to October W4
Final Thesis Writing & Submission (Milestone) | bar: November W4
Project Closure & Archiving | bar: November W4