## Effort Estimates
Efforts and Estimates
Task | Best Effort (hours) | Optimal Effort (hours) | Worst Effort (hours) | Additional Notes
Project Initiation & Planning | 40h | 60h | 120h | Kickoff meeting, define goals, stakeholders, success criteria.
Problem Identification | 24h | 30h | 42h | Document problem statement and scope.
Stakeholder Discussions (initial) | 10h | 15h | 20h | Collect requirements and constraints from stakeholders.
Requirement Analysis | 20h | 25h | 40h | Produce requirement list and acceptance criteria.
Proposal Preparation & Submission | 8h | 10h | 15h | Draft and submit proposal documents.
Business Requirements Document (BRD) | 25h | 30h | 40h | Create BRD; include use cases and data requirements.
Scope Change & Background Research (post-presentation) | 15h | 20h | 30h | Re-evaluate scope; log change requests and impacts.
BRD Update (after scope change) | 2h | 3h | 5h | Re-evaluate scope; log change requests and impacts.
Research & Thesis Writing (ongoing) | 100h | 120h | 200h | Ongoing literature review and thesis drafting.
Data Collection | 25h | 30h | 40h | Collect datasets, obtain consents, and store securely.
Data Cleaning & Preprocessing | 5h | 7h | 10h | Clean, anonymize, and prepare data for analysis.
Exploratory Data Analysis (EDA) | 5h | 7h | 10h | EDA to identify features and data quality issues.
UI Designing for landing page | 5h | 10h | 30h | Figma wireframes and interactive prototypes.
Landing page development | 8h | 10h | 20h
QA & Visual testing for landing page | 3h | 4h | 5h | Run usability tests and collect user feedback.
UI Designing for questionnaire page | 10h | 12h | 20h
Implementation of questionnaire page | 8h | 10h
Complete Guest User Flow | 5h | 8h | 10h | Complete UX for guest journeys and edge cases.
QA & Visual testing for questionnaire flow | 5h | 8h | 10h
UI Designing for guest user disorder severity results dashboard | 10h | 15h | 20h
Implementaion of severity results dashboard | 12h | 16h | 20h
QA and visual testing | 8h | 10h | 12h
UI Design of Login & Sign-up | 5h | 8h | 10h
Login & Sign-up Implementation | 8h | 10h | 20h | Implement authentication, validation, and error flows.
To be Continued
Database Design & Setup | 9600 (160h) | 12000 (200h) | 19200 (320h) | Schema design, migrations, and sample data.
Backend/API Development & Integration | 21600 (360h) | 26400 (440h) | 38400 (640h) | Implement APIs, auth, and endpoints for frontend.
Identity/Consent Integration | 9600 (160h) | 12000 (200h) | 19200 (320h) | Integrate consent capture and identity management.
Develop Agentic Flow (Guest & Employee) | 14400 (240h) | 19200 (320h) | 28800 (480h) | Implement decision flows and state management.
CI/CD Pipeline & Containerization | 16800 (280h) | 21600 (360h) | 33600 (560h) | Automate builds, tests, and deployments (containers).
Feature Engineering | 9600 (160h) | 12000 (200h) | 19200 (320h) | Create features for model input and store versions.
Model Training (XGBoost) | 9600 (160h) | 12000 (200h) | 19200 (320h) | Train XGBoost with cross-validation and logging.
Statistical Validation & Metrics (XGBoost) | 9600 (160h) | 12000 (200h) | 19200 (320h) | Calculate metrics, confidence intervals, and tests.
Disorder Severity Classification Module | 9600 (160h) | 12000 (200h) | 19200 (320h) | Implement classification thresholds and outputs.
Employee Validation & Role Alignment | 7200 (120h) | 9600 (160h) | 14400 (240h) | Align outputs with job roles; validation studies.
Data Insights & Visual Dashboards | 7200 (120h) | 9600 (160h) | 14400 (240h) | Dashboards for stakeholders; KPIs and visualisations.
Security & Privacy Testing | 9600 (160h) | 12000 (200h) | 19200 (320h) | Conduct security review and fix vulnerabilities.
Accessibility Testing (a11y) | 4800 (80h) | 7200 (120h) | 9600 (160h) | Ensure WCAG compliance; fix accessibility issues.
Performance / Load Testing | 9600 (160h) | 12000 (200h) | 19200 (320h) | Load testing and performance tuning.
System Integration Testing | 9600 (160h) | 12000 (200h) | 19200 (320h) | End-to-end integration tests across services.
User Acceptance Testing (UAT) | 9600 (160h) | 12000 (200h) | 19200 (320h) | UAT sessions with stakeholders; collect signoff.
Documentation: Technical & API Docs | 43200 (720h) | 55200 (920h) | 81600 (1360h) | API docs, architecture diagrams, code comments.
Documentation: User Manuals & Training | 14400 (240h) | 16800 (280h) | 24000 (400h) | Create user guides and training material.
Training Sessions & Handover | 7200 (120h) | 9600 (160h) | 14400 (240h) | Deliver training and create handover package.
Progress Viva 1 (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h) | Milestone presentation of initial progress.
Progress Viva 2 (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h) | Second progress review and adjustments.
Final Viva (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h) | Final defence; submit final thesis documents.
System Deployment: Staging | 4800 (80h) | 4800 (80h) | 7200 (120h) | Deploy to staging for QA and demo.
System Deployment: Production | 4800 (80h) | 4800 (80h) | 7200 (120h) | Production rollout with monitoring.
System Testing & Evaluation (full) | 14400 (240h) | 19200 (320h) | 28800 (480h) | Full evaluation against acceptance criteria.
Final Thesis Writing & Submission (Milestone) | 2400 (40h) | 2400 (40h) | 4800 (80h) | Finalize thesis and prepare submission package.
Project Closure & Archiving | 2400 (40h) | 2400 (40h) | 4800 (80h) | Archive artifacts, lessons learned, and signoff.