## Gantt
Task | Start Week Index | End Week Index | Jan W1 | Jan W2 | Jan W3 | Jan W4 | Feb W1 | Feb W2 | Feb W3 | Feb W4 | Mar W1 | Mar W2 | Mar W3 | Mar W4 | Apr W1 | Apr W2 | Apr W3 | Apr W4 | May W1 | May W2 | May W3 | May W4 | Jun W1 | Jun W2 | Jun W3 | Jun W4 | Jul W1 | Jul W2 | Jul W3 | Jul W4 | Aug W1 | Aug W2 | Aug W3 | Aug W4 | Sep W1 | Sep W2 | Sep W3 | Sep W4 | Oct W1 | Oct W2 | Oct W3 | Oct W4 | Nov W1 | Nov W2 | Nov W3 | Nov W4
Problem Identification | 0 | 1 | bar: Jan W1 to Jan W2
Stakeholder Discussions (initial) | 0 | 2 | bar: Jan W1 to Jan W3
Requirement Analysis | 1 | 3 | bar: Jan W2 to Jan W4
Proposal Submission | 3 | 3 | bar: Jan W4
Proposal Presentation | 3 | 3 | bar: Jan W4
Scope Change & Background Research + BRD Update | 4 | 7 | bar: Feb W1 to Feb W4
Research & Thesis Writing (ongoing) | 0 | 26 | bar: Jan W1 to Jul W3
Start Research Work & Thesis Writing (intensive) | 4 | 28 | bar: Feb W1 to Aug W1
Data Collection | 4 | 15 | bar: Feb W1 to Apr W4
UI Designing (Figma) | 6 | 11 | bar: Feb W3 to Mar W4
Complete Guest User Flow | 10 | 13 | bar: Mar W3 to Apr W2
Login & Sign-up | 12 | 15 | bar: Apr W1 to Apr W4
Agentic Flow (Guest & Employee) | 14 | 21 | bar: Apr W3 to Jun W2
ML (XGBoost) Statistical Validation | 20 | 25 | bar: Jun W1 to Jul W2
Disorder Severity Classification | 24 | 29 | bar: Jul W1 to Aug W2
Employee Validation & Role Alignment | 28 | 31 | bar: Aug W1 to Aug W4
Data Insights & Visual Dashboards | 30 | 33 | bar: Aug W3 to Sep W2
Progress Viva 1 | 15 | 15 | bar: Apr W4
Progress Viva 2 | 30 | 30 | bar: Aug W3
System Testing & Evaluation | 32 | 39 | bar: Sep W1 to Oct W4
Final Viva & Final Thesis Submission | 43 | 43 | bar: Nov W4
Final Thesis Submission (document) | 43 | 43 | bar: Nov W4
Supervisor Meetings & Feedback (biweekly) | 1 | 43