## Gantt - Full
[28 empty] | Tasks to be done | [8 empty] | Completed tasks
Task | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Project Initiation & Planning | bar: January W1 to January W2
Problem Identification | bar: January W1
Stakeholder Discussions (initial) | bar: January W1 to January W3
Supervisor Meetings & Feedback (biweekly)
Requirement Analysis | bar: January W2 to January W4
Proposal Preparation & Submission | bar: January W3 to January W4
Proposal Presentation (Milestone) | bar: January W4
Business Requirements Document (BRD) | bar: January W4 to February W3
Scope Change & Background Research (post-presentation) | bar: February W1 to March W1
BRD Update (after scope change) | bar: February W2 to March W1
Ethics / IRB Approval (if required) | bar: February W1 to March W2
Data Governance & Privacy Plan | bar: February W1 to March W2
Research & Thesis Writing (ongoing) | bar: January W1 to August W3
Start Research Work & Thesis Writing (intensive) | bar: February W1 to August W3
Data Collection | bar: February W1 to April W4
Data Cleaning & Preprocessing | bar: March W1 to May W3
Exploratory Data Analysis (EDA) | bar: March W2 to June W1
UI Designing (Figma) | bar: February W3 to March W4
Prototyping & Usability Testing | bar: March W2 to April W2
Complete Guest User Flow (UX) | bar: March W3 to April W2
Login & Sign-up Implementation | bar: April W1 to April W4
Database Design & Setup | bar: March W3 to April W3
Backend/API Development & Integration | bar: April W1 to June W3
Identity/Consent Integration | bar: April W3 to May W3
Develop Agentic Flow (Guest & Employee) | bar: April W3 to June W2
CI/CD Pipeline & Containerization | bar: June W1 to August W1
Feature Engineering | bar: May W3 to June W3
Model Training (XGBoost) | bar: June W1 to July W1
Statistical Validation & Metrics (XGBoost) | bar: June W3 to July W3
Disorder Severity Classification Module | bar: July W1 to August W1
Employee Validation & Role Alignment | bar: August W1 to August W4
Data Insights & Visual Dashboards | bar: August W3 to September W2
Security & Privacy Testing | bar: September W1 to October W1
Accessibility Testing (a11y) | bar: September W2 to September W4
Performance / Load Testing | bar: September W3 to October W3
System Integration Testing | bar: September W1 to October W1
User Acceptance Testing (UAT) | bar: October W1 to November W1
Documentation: Technical & API Docs | bar: May W3 to November W1
Documentation: User Manuals & Training | bar: September W3 to November W1
Training Sessions & Handover | bar: October W4 to November W3
Progress Viva 1 (Milestone) | bar: April W4
Progress Viva 2 (Milestone) | bar: August W2
Final Viva (Milestone) | bar: November W4
System Deployment: Staging | bar: August W3 to August W4
System Deployment: Production | bar: November W1 to November W2
System Testing & Evaluation (full) | bar: September W1 to October W4
Final Thesis Writing & Submission (Milestone) | bar: November W4
Project Closure & Archiving | bar: November W4