## Sheet1
Sprint 0
Task | Start Date | End Date | Best Effort (minutes/hours) | Optimal Effort (minutes/hours) | Worst Effort (minutes/hours) | Notes
Project Initiation & Planning | 2026-01-01 | 2026-01-14 | 4800 (80h) | 6000 (60h) | 7200 (120h) | Kickoff meeting, define goals, stakeholders, success criteria.
Problem Identification | 2026-01-01 | 2026-01-07 | 2400 (40h) | 3000 (30h) | 4800 (80h) | Document problem statement and scope.
Stakeholder Discussions (initial) | 2026-01-01 | 2026-01-21 | 4800 (80h) | 7200 (120h) | 9600 (160h) | Collect requirements and constraints from stakeholders.
Supervisor Meetings & Feedback (biweekly) | 2026-01-01 | 2026-11-04 | 84000 (1400h) | 105600 (1760h) | 158400 (2640h) | Biweekly meetings with supervisor for feedback and direction.
Requirement Analysis | 2026-01-08 | 2026-01-28 | 4800 (80h) | 7200 (120h) | 9600 (160h) | Produce requirement list and acceptance criteria.
Proposal Preparation & Submission | 2026-01-15 | 2026-01-28 | 4800 (80h) | 4800 (80h) | 7200 (120h) | Draft and submit proposal documents.
Proposal Presentation (Milestone) | 2026-01-15 | 2026-01-28 | 4800 (80h) | 4800 (80h) | 7200 (120h) | Draft and submit proposal documents.
Business Requirements Document (BRD) | 2026-01-22 | 2026-02-18 | 7200 (120h) | 9600 (160h) | 14400 (240h) | Create BRD; include use cases and data requirements.
Scope Change & Background Research (post-presentation) | 2026-01-29 | 2026-03-04 | 9600 (160h) | 12000 (200h) | 19200 (320h) | Re-evaluate scope; log change requests and impacts.
BRD Update (after scope change) | 2026-01-22 | 2026-02-18 | 7200 (120h) | 9600 (160h) | 14400 (240h) | Create BRD; include use cases and data requirements.
Ethics / IRB Approval | 2026-01-29 | 2026-03-11 | 12000 (200h) | 14400 (240h) | 21600 (360h) | Prepare and submit ethics/IRB application if needed.
Data Governance & Privacy Plan | 2026-01-29 | 2026-03-11 | 12000 (200h) | 14400 (240h) | 21600 (360h) | Define consent, storage, anonymization, retention policies.
Research & Thesis Writing (ongoing) | 2026-01-29 | 2026-03-04 | 9600 (160h) | 12000 (200h) | 19200 (320h) | Re-evaluate scope; log change requests and impacts.
Start Research Work & Thesis Writing (intensive) | 2026-01-29 | 2026-08-05 | 52800 (880h) | 64800 (1080h) | 96000 (1600h) | Begin experiments and write initial chapters.