## Backlog
Sprint | Epic Number | Epic Name | Feature | User Story | Story # in Epic | Start Date | End Date | Notes
| E1 | Landing page | Application entry point | Designing the landing page
Sprint 1 | E1 | Guest user flow | Browse as guest; view questionnaires | As a guest I would like to interact with sample questionnaires | 1 | 2026-02-12 | 2026-02-25 | Complete guest path, no auth required.
Sprint 1 | E1 | Guest user flow | Browse as guest; view questionnaires | As a guest I can start a screening survey without signup | 2 | 2026-02-12 | 2026-02-25 | Complete guest path, no auth required.
Sprint 1 | E1 | Guest user flow | Browse as guest; view questionnaires | As a guest I can see severity evaluation dashboard and save answers temporarily | 3 | 2026-02-12 | 2026-02-25 | Complete guest path, no auth required.
Sprint 1 | E1 | Guest user flow | Agentic chat | As a guest I would like ti interact with agentic chat | 4
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I would like to register with email | 1 | 2026-02-12 | 2026-02-25 | Include basic validation and session handling.
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I would like to get successfully authenticated to the system | 2 | 2026-02-12 | 2026-02-25 | Include basic validation and session handling.
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I would like to get successfully authorized to the system | 3 | 2026-02-12 | 2026-02-25 | Include basic validation and session handling.
Sprint 1 | E2 | Login & Signup | Authentication and authorization | As a user I need to reset my password as required