## Backlog
Sprint | Epic Number | Epic Name | Feature | User Story | Start Date | End Date | Notes
Sprint 4 | E4 | ML Statistical Validation | Model evaluation & metrics | As a data scientist I can run validation metrics | 2026-03-11 | 2026-03-24 | Batch evaluation and reporting.
Sprint 4 | E4 | ML Statistical Validation | Model evaluation & metrics | As a stakeholder I can view model AUC/precision/recall | 2026-03-11 | 2026-03-24 | Batch evaluation and reporting.
Sprint 4 | E4 | ML Statistical Validation | Model evaluation & metrics | As a maintainer I can export validation reports | 2026-03-11 | 2026-03-24 | Batch evaluation and reporting.
Sprint 5 | E5 | Disorder Severity Evaluation | Severity scoring & thresholds | As a clinician I can see severity scores per user | 2026-03-11 | 2026-03-24 | Link to scoring service.
Sprint 5 | E5 | Disorder Severity Evaluation | Severity scoring & thresholds | As a clinician I can adjust thresholds for severity bands | 2026-03-11 | 2026-03-24 | Link to scoring service.
Sprint 5 | E5 | Disorder Severity Evaluation | Severity scoring & thresholds | As an analyst I can view score distributions | 2026-03-11 | 2026-03-24 | Link to scoring service.
Sprint 6 | E7 | Severity Calibration
Sprint 7 | E8 | Clinician verification
Sprint 8 | E9 | HR Employee Validation | HR review & validation of records | As HR I can search employee records | 2026-02-26 | 2026-03-10 | Access control for HR roles.
Sprint 9 | E10 | HR Employee Validation | HR review & validation of records | As HR I can validate submitted questionnaires | 2026-02-26 | 2026-03-10 | Access control for HR roles.
Sprint 2 | E11 | HR Employee Validation | HR review & validation of records | As HR I can flag records for follow-up | 2026-02-26 | 2026-03-10 | Access control for HR roles.
Sprint 3 | E7 | Data Insights | Dashboards and exports | As a manager I can view aggregated insights | 2026-03-11 | 2026-03-24 | Start with key dashboards (screening counts, severity).
Sprint 3 | E7 | Data Insights | Dashboards and exports | As a user I can download my summary report | 2026-03-11 | 2026-03-24 | Start with key dashboards (screening counts, severity).
Sprint 3 | E7 | Data Insights | Dashboards and exports | As a researcher I can export anonymized datasets | 2026-03-11 | 2026-03-24 | Start with key dashboards (screening counts, severity).