## Product Backlog
ID | Epic | Feature | User Story 1 | User Story 2 | Priority | Owner | Best (min) | Optimal (min) | Worst (min)
PBI-001 | E1 | Account registration | As a new user, I can create an account. | As a new user, I can choose my role during sign-up. | Must | apps/web-frontend + identity-consent-service | 480 | 720 | 1080
PBI-002 | E1 | Secure sign-in | As a user, I can log in with valid credentials. | As a user, I get clear error messages for failed login. | Must | apps/web-frontend + identity-consent-service | 480 | 720 | 1080
PBI-003 | E1 | Session control | As a user, I stay logged in safely while active. | As a user, I can log out from any page. | Must | apps/web-frontend | 360 | 540 | 840
PBI-004 | E2 | Consent preferences | As a data subject, I can select what data can be shared. | As a data subject, I can set how long sharing is allowed. | Must | apps/identity-consent-service | 600 | 900 | 1320
PBI-005 | E2 | Access permission checks | As an admin, I can enforce role-based access. | As an admin, I can enforce purpose-based access checks. | Must | apps/identity-consent-service | 720 | 1080 | 1560
PBI-006 | E2 | Consent cancellation | As a privacy officer, I can revoke consent immediately. | As a privacy officer, I can block new access after revocation. | Must | apps/identity-consent-service + apps/integration-service | 720 | 1080 | 1680
PBI-007 | E3 | Combined profile page | As a clinician, I can view clinical and work context together. | As an HR manager, I can view the same profile with allowed fields. | Must | apps/profile-case-service | 720 | 1080 | 1560
PBI-008 | E3 | Case status tracking | As a coordinator, I can create a case record. | As a coordinator, I can move a case from intake to closure. | Must | apps/profile-case-service | 900 | 1320 | 1920
PBI-009 | E3 | Case event timeline | As a user, I can view key events in time order. | As a user, I can filter timeline events by type. | Should | apps/profile-case-service + apps/web-frontend | 720 | 1080 | 1680
PBI-010 | E4 | Screening form submission | As an employee, I can submit screening answers. | As an employee, I can receive risk and severity results. | Must | apps/ai-screening-service | 720 | 1080 | 1560
PBI-011 | E4 | Clinician confirmation labels | As a clinician, I can submit confirmed labels. | As a clinician, I can override AI results with a reason. | Must | apps/ai-screening-service | 600 | 900 | 1320
PBI-012 | E4 | Pilot data export | As governance staff, I can export screening data. | As governance staff, I can export clinician label data in one file. | Must | apps/ai-screening-service | 480 | 720 | 1080
PBI-013 | E4 | Threshold adjustment | As calibration staff, I can change model thresholds. | As calibration staff, I can enforce minimum specificity rules. | Should | apps/ai-screening-service | 600 | 900 | 1440
PBI-014 | E5 | Accommodation planning | As an HR manager, I can create an accommodation plan. | As an HR manager, I can link plan items to clinical needs. | Must | apps/profile-case-service | 720 | 1080 | 1560
PBI-015 | E5 | Role requirement mapping | As HR, I can map job demands to cognitive requirements. | As HR, I can use this map for role-fit checks. | Must | apps/profile-case-service | 720 | 1080 | 1560
PBI-016 | E5 | Accommodation adherence view | As a manager, I can track accommodation usage. | As a manager, I can review effectiveness over time. | Should | apps/profile-case-service | 600 | 900 | 1440
PBI-017 | E6 | Cross-service workflow engine | As the platform, I can run workflow steps across services. | As the platform, I can track each step status. | Must | apps/integration-service | 900 | 1320 | 1980
PBI-018 | E6 | Unified recommendation request | As a coordinator, I can request recommendations from clinical inputs. | As a coordinator, I can include HR inputs in the same request. | Must | apps/integration-service | 840 | 1260 | 1860
PBI-019 | E6 | Recommendation conflict alerts | As a coordinator, I can detect conflicts between recommendations. | As a coordinator, I can see conflict details clearly. | Must | apps/integration-service | 720 | 1080 | 1620
PBI-020 | E6 | Intervention what-if comparison | As a board member, I can compare intervention options. | As a board member, I can view trade-offs side by side. | Should | apps/integration-service | 900 | 1380 | 2100
PBI-021 | E7 | KPI dashboard metrics | As an analyst, I can view alignment and latency KPIs. | As an analyst, I can view outcome KPIs for reports. | Must | apps/ai-analytics-service | 720 | 1080 | 1620
PBI-022 | E7 | Drift and fairness monitoring | As governance staff, I can monitor model drift. | As governance staff, I can monitor fairness alerts. | Should | apps/ai-analytics-service | 720 | 1080 | 1740
PBI-023 | E7 | Recommendation reason records | As governance staff, I can see why a recommendation was made. | As governance staff, I can review explanation records later. | Should | apps/ai-analytics-service | 600 | 900 | 1440
PBI-024 | E7 | Cohort insight analysis | As an analytics lead, I can analyze by condition and severity. | As an analytics lead, I can analyze by role group. | Could | apps/ai-analytics-service | 720 | 1140 | 1860
PBI-025 | E8 | Role-based notifications | As a clinician, I receive important event alerts. | As an HR manager, I receive important event alerts for my role. | Should | apps/notification-service | 480 | 720 | 1140
PBI-026 | E8 | Pending task inbox | As a user, I can view pending review tasks. | As a user, I can view pending approval and follow-up tasks. | Should | apps/notification-service + apps/web-frontend | 600 | 900 | 1380
PBI-027 | E8 | Critical case escalation rules | As governance staff, I can define escalation rules. | As governance staff, I can apply rules to unresolved critical cases. | Could | apps/notification-service | 600 | 960 | 1500
PBI-028 | E9 | Stable API contract versions | As an integrator, I can use versioned API contracts. | As an integrator, I can use matching schema files. | Must | packages/api-contracts + apps/gateway-service | 600 | 900 | 1380
PBI-029 | E9 | Reliable case events | As operations staff, I can publish domain events. | As operations staff, I can consume domain events reliably. | Must | apps/integration-service | 720 | 1080 | 1620
PBI-030 | E9 | External system connectors | As the platform, I can sync with EHR systems. | As the platform, I can sync with HRIS systems. | Should | apps/integration-service | 960 | 1500 | 2340
PBI-031 | E10 | Role home pages | As a user, I can access my role page after login. | As a user, I see employee, clinician, HR, or calibration views. | Must | apps/web-frontend | 600 | 900 | 1320
PBI-032 | E10 | Employee screening flow UI | As an employee, I can complete screening step by step. | As an employee, I can review answers before submit. | Must | apps/web-frontend | 720 | 1080 | 1560
PBI-033 | E10 | Clinician review workspace UI | As a clinician, I can review case evidence in one page. | As a clinician, I can submit labels from the same page. | Must | apps/web-frontend | 720 | 1080 | 1560
PBI-034 | E10 | HR planning dashboard UI | As HR, I can manage accommodation plans. | As HR, I can manage role-fit plans from one dashboard. | Must | apps/web-frontend | 720 | 1080 | 1620
PBI-035 | E10 | Leadership analytics workspace UI | As leadership, I can view KPI dashboards. | As leadership, I can view calibration dashboards in one place. | Should | apps/web-frontend | 720 | 1140 | 1740
PBI-036 | E11 | Access audit trail | As compliance staff, I can log every data access event. | As compliance staff, I can capture user, purpose, time, and case ID. | Must | Cross-cutting | 720 | 1080 | 1680
PBI-037 | E11 | Encryption and key lifecycle | As security staff, I can encrypt data in transit and at rest. | As security staff, I can rotate encryption keys on schedule. | Must | infrastructure + Cross-cutting | 840 | 1260 | 1920
PBI-038 | E11 | Data retention and deletion rules | As a privacy officer, I can set retention rules by data type. | As a privacy officer, I can enforce deletion rules by data type. | Should | Cross-cutting | 600 | 900 | 1500
PBI-039 | E12 | CI quality and security checks | As DevOps, I can run tests and contract checks in CI. | As DevOps, I can run security scans in CI gates. | Must | infrastructure + all apps | 840 | 1260 | 1860
PBI-040 | E12 | Reliability monitoring stack | As SRE, I can monitor traces, errors, and latency. | As SRE, I can monitor backups and recovery readiness. | Must | infrastructure + all apps | 960 | 1440 | 2160
E7 | run cohort analysis by condition, severity, role, and intervention type | As analytics lead, I can run cohort analysis by condition, severity, role, and intervention type.